## IRMS Project
IMS Action Plan
[5 empty] | WEEK | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| # | Task | Time | Who | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1900-01-18 | 1900-01-25 | 1900-02-01 | 1900-02-08 | 1900-02-15 | 1900-02-22 | 1900-03-01 | 1900-03-08 | 1900-03-15 | Note
#VALUE! | STAGE 1: Review and Evaluate Current Systems, including:
#VALUE! | 1.1 | Gap Analysis Audit | 2 days |  | Complete | [11 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
STAGE 2: Design and Development of IMS Documentation as per Action Plan
| 2.1 | Hazards and Risk:Coach/train personnel in JSA and Plant Risk Assessment. Support staff to complete JSAs/ Plant Risk Assessments | 2 days |  | Planned | Target Completion
| 2.2 | Environmental Aspects/ Impacts: develop Register or incorporate in SWMS. | 0.5 days
| 2.3 | Legal Requirements: develop Legal Register (OHS and environment), procedure and undertake evaluation | 2 days
| 2.4 | Legal Requirements: Ensure periodical compliance requirements (e.g. fire testing, chains, slings, crane testing) all in software to flag as event. | 0.5 days
| 2.5 | Objectives and Targets: Identify potential OHSEQ targets and commence monitoring | 2 hours
| 2.6 | Roles and Responsibilities: Review current statements to ensure OHSEQ responsibilities reflect current practice. | 2 hours
| 2.7 | Competency and Training: Enter current training, competency and licencing data in software (OHS&E). | 1.5 to 2 days
| 2.8 | Competency and Training: develop introduction to IMS for incorporation in induction. | 2 hours
| 2.9 | Documentation: Integrate and develop as per Report. | 2 days
| 2.1 | Document and Record Control: develop procedure and record matrix as per Report (matrix may not be required if functionality in software) | 0.5 days
| 2.11 | Product Realisation (ISO 9001): Confirm preventive maintenance and calibration tasks in software or equivalent. Develop overview Manual for Manufacturing and Field Services (based on existing information). | 1.5 days
| 2.12 | Emergency Preparedness: Develop emergency response plan (if not existing). If existing - review to ensure covers environment related events | 0.5 days
| 2.13 | Incident/Corrective/Preventive Action: Confirm why manually recorded (rather than direct to software). Integrate procedure in IMS Manaul. | 2 hours
| 2.14 | Internal Audit: Develop procedure, schedule. | 2 hours
STAGE 3: Implement Integrated IMS (Refer "Addressing Gaps" in Gap Analysis Report)
| 3.1 | Refer "Addressing Gaps" in Gap Analysis Report. Includes: • Overview training in: - Hazard and risk assessment. - Management systems. - Basic legal requirements (do not pollute etc.). - Their role and responsibilities. - Incident reporting and corrective action. | 1 day
| 3.2 | • Nominated personnel should also be trained in Internal Auditing. | 2 hours
| 3.3 | • Training in use of the preferred platform. | 1.5 days recommended for 2-3 key users; 1 hour session for general users (* 3 sessions to cover all staff)
| 3.4 | • A full internal audit of the IMS is required prior to Certification (can be combined with training of internal auditors). • An evaluation of compliance (conducted via an internal audit) is also required prior to Certification. | 0.75 of day
| 3.5 | Management Review of IMS (prior to Certification) | 1.5 hours
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!